## Table 2
Table Name | SRAM Type | HD6T | HC6T | 8T2P | DP
Table: SRAM Bitcell 定义 | Bitcell Area\ /um^2 | 0.110 | 0.124 | 0.185 | 0.274

## Table 3 (1)
Table Name | Index | Memory Compiler | Bitcell Type
Table: Vendor A Memory Compiler 定义 | P1 | High Speed One Port Register File | DICE
| P2 | Ultra High Density Single Port SRAM Compiler | DICE

## Table 3
Table Name | Index | Memory Compiler | Bitcell Type
Table: Memory Compiler 定义 | P1 | High Speed One Port Register File | DICE
| P2 | Ultra High Density Single Port SRAM Compiler | DICE

## Table4 (3)
Table Name | Column\ Mux | Bank | Word\ Step | Word\ Min | Word\ Max | Bit\ Step | Bit\ Min | Bit\ Max | Maximum\ Density
Table: High Speed One Port Register File 容量范围定义 | 2 | 1 | 8 | 16 | 512 | 2 | 8 | 288 | 144Kb
| 2 | 2 | 8 | 32 | 1024 | 2 | 8 | 288 | 288Kb
| 4 | 1 | 16 | 32 | 1024 | 1 | 8 | 144 | 144Kb
| 4 | 2 | 16 | 64 | 2048 | 1 | 8 | 144 | 288Kb

## Table4 (8)
Table Name | Column\ Mux | Bank | Word\ Step | Word\ Min | Word\ Max | Bit\ Step | Bit\ Min | Bit\ Max | Maximum\ Density
Table: Ultra High Density Single Port SRAM Compiler 容量范围定义 | 4 | 1 | 16 | 32 | 1024 | 1 | 8 | 320 | 320Kb
| 4 | 2 | 16 | 64 | 2048 | 1 | 8 | 320 | 640Kb
| 4 | 4 | 16 | 128 | 4096 | 1 | 8 | 320 | 1.25Mb
| 4 | 8 | 16 | 256 | 8192 | 1 | 8 | 320 | 2.5Mb
| 8 | 1 | 32 | 64 | 2048 | 1 | 8 | 160 | 320Kb
| 8 | 2 | 32 | 128 | 4096 | 1 | 8 | 160 | 640Kb
| 8 | 4 | 32 | 256 | 8192 | 1 | 8 | 160 | 1.25Mb
| 8 | 8 | 32 | 512 | 16384 | 1 | 8 | 160 | 2.5Mb
| 16 | 1 | 64 | 128 | 4096 | 1 | 8 | 80 | 320Kb
| 16 | 2 | 64 | 256 | 8192 | 1 | 8 | 80 | 640Kb
| 16 | 4 | 64 | 512 | 16384 | 1 | 8 | 80 | 1.25Mb
| 16 | 8 | 64 | 1024 | 32768 | 1 | 8 | 80 | 2.5Mb

## Table 5
Table Name | Corners | Process | VDD(V) | Temp(C) | RCtype
Table: Characterization Corner 规格 | TT0P8V25CTT | TT | 0.8 | 25 | Nominal
| TT0P8V85CTT | TT | 0.8 | 85 | Nominal
| SSGNP0P72VN40CJJ | SSGNP | 0.72 | -40 | FuncCmax
| SSGNP0P72V125CJJ | SSGNP | 0.72 | 125 | FuncCmax
| FFGNP0P88VN40CJJ | FFGNP | 0.88 | -40 | FuncCmin
| FFGNP0P88V125CJJ | FFGNP | 0.88 | 125 | FuncCmin

## Table 6
Table Name | File | Contains
Table: EDA View规格 | Netlist (*.cir) | Instance SPICE netlist for LVS.
| GDSII (*.gds) | Instance GDSII file.
| Datasheet (*.ds) | Instance datasheet, provides timing characterization, read and write cycle timing, and power dissipation.
| Verilog (*.v) | Instance Verilog model.
| LEF (*.lef) | Instance LEF description of ring structure.
| Liberty (*.lib) | Synopsys synthesis nldm timing model.
| CCS Liberty (*_ccsm.lib) | Synopsys synthesis ccs timing model.
| CCSN Liberty (*_ccsn.lib) | Synopsys synthesis ccs noise timing model.
| ECSM Liberty (*_ecsm.lib) | Effective Current Source Model.
| Tetra Max (*.tmax) | Synopsys TetraMax model.
| Mbist (*.memlib) | Tessent Memory BIST model.
| ATPG(*.fastscan) | Tessent atpg model
| CPF(*.cpf) | Common Power Format
| UPF(*.upf) | Unified Power Format.
| AVM (*.avmcfg) | Redhawk EMIR model.
| Bitmap(*.bitmap) | Memory model for MBIST diagnostic.
| Masis(*.masis) | Synopsys SMS Memory BIST model.
| Yaml Data(*.dml) | Summarize the data from timing model.
| Emulation model(*_emu.v) | Synthesizable Verilog model.

## Table 7
Table Name | Testchip Code | KWS10
Table: 第一阶段测试片信息 | PDK Version | GF22nm(TBD)
| Metal Stack | 1P8M(TBD)
| Package | TFBGA(TBD)
| Size | ~2mm*2mm(TBD)

## Table 8
Table Name | Phase | Task | Start Date | End Date
Table: 第一阶段测试片开发计划 | 1 | KICK OFF | 2026/7/20 | 2026/7/31
| 2 | SRAM Compiler IP Initial Release | 2026/7/20 | 2026/7/31
| 3 | RTL Design & Simulation | 2026/8/1 | 2026/8/15
| 4 | Verification | 2026/8/15 | 2026/8/25
| 5 | SRAM Compiler IP Final Release | 2026/10/10 | 2026/10/15
| 6 | PR | 2026/8/22 | 2026/11/15
| 7 | Post-Simulation | 2026/10/15 | 2026/11/15
| 8 | Sign off | 2026/11/15 | 2026/11/25
| 9 | Tape out | 2026/11/25 | 2026/11/30

## Table 9
Table Name | Phase | Task | Date
Table: 第一阶段封装测试计划 | 1 | Wafer out | T0
| 2 | Testchip Package | T0 + 1.5 month
| 3 | Testchip Loadboard | T0 + 2 month
| 4 | Testchip Test | T0 + 3.5 month
| 5 | Testchip Report | T0 + 3.5 month
| 6 | Testchip Test(Radiation Resistance) | T0 + 5.5 month
| 7 | Testchip Report(Radiation Resistance) | T0 + 5.5 month

## Table 10
Table Name | Testchip Code | KWS10
Table: 第二阶段测试片信息 | PDK Version | SOI 22nm(TBD)
| Metal Stack | 1P8M(TBD)
| Package | TFBGA(TBD)
| Size | ~5mm*5mm(TBD)

## Table 11
Table Name | Phase | Task | Start Date | End Date
Table: 第二阶段测试片开发计划 | 1 | KICK OFF | 2026/12/1 | 2026/12/05
| 2 | SRAM Compiler IP Initial Release | 2026/12/15 | 2026/12/20
| 3 | RTL Design & Simulation | 2026/12/01 | 2027/1/31
| 4 | Verification | 2027/1/15 | 2027/2/15
| 5 | SRAM Compiler IP Final Release | 2027/3/15 | 2027/3/20
| 6 | PR | 2027/3/1 | 2027/6/1
| 7 | Post-Simulation | 2027/6/1 | 2027/6/15
| 8 | Sign off | 2027/6/15 | 2027/6/25
| 9 | Tape out | 2027/6/25 | 2027/6/30

## Table 12
Table Name | Phase | Task | Date
Table: 第二阶段封装测试计划 | 1 | Wafer out | T0
| 2 | Testchip Package | T0 + 1.5 month
| 3 | Testchip Loadboard | T0 + 2 month
| 4 | Testchip Test | T0 + 3.5 month
| 5 | Testchip Report | T0 + 3.5 month
| 6 | Testchip Test(Radiation Resistance) | T0 + 5.5 month
| 7 | Testchip Report(Radiation Resistance) | T0 + 5.5 month